## Introduction
The purpose of this spread sheet is to provide a summary of SAE J1699-5 Task Force work items and a list of pending software changes.
The J1699-5 applciation can be found at https://portal.autosinnovate.org/obd-certification-public-access/
The SAE J1699-5 Task Force Chairman is Mark Zackos. Mark's e-mail address is mark@dgtech.com
Software questions/issues can be directed to Kevin Stofflet at kstofflet@engenius.com.
Last Value
J1699-3 Issue Numbers that have also been fixed in J1699-5 | 3-xxxx
J1699-5 Issue Numbers | 5-10099

## J1699-5 Task Force Work Items
Type | Issue Number | Description | Requestor | Open Date | Accept Date | Priority/ Release | Close Date | Status
Items Pending Review
Discussion | Not Assigned | Need to clarify if $F501 must e supported by 'at least one ECU' or 'all ECUs'. | KStofflet | 2024-11-14 |  |  |  |  | T
Discussion | Not Assigned | ISO 13400 allows for a NAK with DoIP Version set to $00 if the DoIP version requested is not supported. J1699-5 currently uses DoIP Version $02. Does J1699-5 need to check for 3 and 4 in this case? | KStofflet | 2024-10-17 |  |  |  |  | T
Bug Fix | 3-1104 | Test 10.12 The prompt should say "(BARO > 22 in Hg)", but it currently says "(BARO < 22 in Hg)". | Bosch | 2024-10-24 |  | 04.04.00 | 2024-11-13 | Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 3-1103 | The prompt for Vehicle Type says "3 Medium Duty Truck Engine Dyno Certified (< 1400 lbs GVWR)", but it should be 14000. | john.v.bowman@gm.com | 2024-10-16 |  | 04.04.00 | 2024-11-13 | Fixed in V04.04.00, dated 11/13/2024. | PTI
Add Feature | 3-1102 | Update PID $1C to decode up to $3B. Specifically add Brazil OBD Phase 8 (PID 1C with value of $2F) and Brazil OBD Phase 7 with IUMPR (PID 1C with value of $2A). | DRober44@Ford.Com | 2024-10-08 |  | 04.04.00 | 2024-11-13 | Added in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10099 | Test 7.4 Fails if all F501 responses don't indicate that MIL is active. | shikha.rathi@volvo.com | 2024-10-24 |  |  |  | This functionality is not in requirements… should it be (except that the ECU reporting DTC must also indicate MIL active via F501). | T | SHOULD THE DOCUMENT BE CHANGED
Bug Fix | 5-10098 | Test 10.11 - Crash because ECU IDs don't match original list. | shikha.rathi@volvo.com | 2024-10-24 |  |  |  | Need to check Protocol Determination to insure it handles a change in ECU response order. Also, log shows strange ECU IDs (0x50925602) in data decode for F882 and SMAD responses, but not in link traffic for either. This is the same ID noted in Test 10.11 failure. It seems as if Test 10.10 is corrupting the list of ECUs. | T
Add Feature | 5-10097 | Test 10.7, Add support for Test Results (SID $22 $F6xx). | KStofflet | 2024-10-29 |  |  |  |  | T
Add Feature | 5-10096 | Test 12 Add support CAN on ZEVs. | KStofflet | 2024-10-28 |  | 04.04.00 | 2024-11-13 | Added in V04.04.00, dated 11/13/2024. | PTI
Add Feature | 5-10095 | Add Freeze Frame functionality for ICE. | KStofflet | 2024-10-28 |  |  |  |  | T
Add Feature | 5-10094 | Fail if no NRC for a physical request of a DID that is not supported. | KStofflet | 2024-10-28 |  | 04.04.00 | 2024-11-13 | Added in V04.04.00, dated 11/13/2024. | T
Bug Fix | 5-10093 | In Test 5.16 the overall test FAILs but no faiure is noted for a specific item (in the log). However, there are WARNINGs noted. | ridey_wang@jp.honda | 2024-10-08 |  |  |  |  | T
Bug Fix | 5-10092 | Test 5.17 Group Request versus Single Request for DID $F501 reports: SID $22 group/single DID size mismatch (Response = 8 bytes Expected = 26554 bytes) | wolfgang.reichle@mercedes-benz.com | 2024-10-17 |  | 04.04.00 | 2024-11-13 | Is his related to single ECU with only one DID supported in $F500 ($F501)? Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10091 | DoIP returning a NAK with Unknown Target Address to the $22 $F810 request. | john.v.bowman@gm.com | 2024-10-17 |  | No Change | 2024-10-25 | This is a vehicle issue. | T
Add Feature | 5-10090 | Require NRC for a functional SID $22 DID $F401, $F402, $F441 - if not supported. | john.v.bowman@gm.com | 2024-10-11 |  | 04.04.00 | 2024-11-13 | Added in V04.04.00, dated 11/13/2024. | T
Bug Fix | 5-10089 | DoIP Routing Activation is failing on a ZEV. | john.v.bowman@gm.com | 2024-10-11 |  |  | HOLD - DEBUGGING | Are we switching from UDP to TCP/IP? When starting DoIP communication, StartDoIPChannel() shoud not PASS if RoutingActivation() fails. | T
Document | 5-10088 | In Test 5.16 (can be 200 sec after clear codes) a Warning/Failure for EOE-A ($F818, $F841, $F845) may need to allow for 0 as some engines may take up to 1236 seconds to generate 1kWh (or 123.6 seconds for 0.1kWh). | brandon.apple@volvo.com | 2024-10-09 |  |  | NEED DOC. UPDATE |  | T | If this is accepted, it msut be added to J1699-3.
Add Feature | 5-10087 | In Test 5.16 (can be 200 sec after clear codes) a Warning/Failure for $F841 VFC-A, $F842 EFC-A, and IEFC-A when value is 0 does not make sense. Resolution is 0.5L per bit and the engine cannot consume 0.5L in ~200 sec since code clear. | shikha.rathi@volvo.com | 2024-10-08 |  | 04.04.00 | 2024-11-13 | Added in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10086 | Warnings for $F845 EOE should have the units of GWh NOT sec. | shikha.rathi@volvo.com | 2024-10-08 |  | 04.04.00 | 2024-11-13 | Search code for: Line 7357 & 7364 - "ECU %X INF $F845 EOE-L must return a value of greater than 1 sec" Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10085 | Warnings for $F841 EOE should have the units of MWh NOT sec. | shikha.rathi@volvo.com | 2024-10-08 |  | 04.04.00 | 2024-11-13 | Search code for: Line 7336 & 7342 - "ECU %X INF $F841 EOE-A must return a value of greater than 1 sec" Fixed in V04.04.00, dated 11/13/2024. | PTI
Open Items
Discussion | Not Assigned | What about NRCs that are not identified in Table B, are they allowed? For example SID $22 DIDs F400-F5FF, there is no indication that NRC $21 is not allowed. | shikha.rathi@volvo.com | 2024-05-15 | 2024-05-17 |  | NEED DOC. UPDATE | 5/17/2024 - Task Force to investigate and make decision. | T
Discussion | Not Assigned | Are all UDS OBD II ECU required to respond to 22 F400 and 22 F500 as J1979-2 indicates? Do we need test cases to compare ECUs list to 22 F810? | Mark.Wine@opusivs.com | 2023-01-03 | 2023-01-13 |  |  | 1/13/2023 - Task Force will send this to the Small Group for consideration. | T
Discussion | Not Assigned | The Group PID request from J1699-3 are missing from the document. | J1699 | 2022-12-19 | 2023-01-13 |  |  | 1/13/2023 - Task Force will send this to the Small Group for consideration. | T
Document | 5-10082 | The wording of PASS and FAIL criteria for Test 5.4.1 seems to conflict - If all ECUs must support $F501 to PASS, then shouldn't the FAIL criteria be "One or more Primary DEC EC[P]U that has indicated DID $F501 as supported" | john.v.bowman@gm.com | 2024-09-19 | 2024-10-04 |  | NEED DOC. UPDATE | DOCUMENT ISSUE ONLY - Here is current text: Value Description Pass Positive response from All Primary DEC EC[P]Us that have indicated DID $F501 as supported #DTCs present in all response messages should be zero MIL should be commanded off in all response messages Fail No response from any Primary DEC EC[P]U that has indicated DID $F501 as supported Non-zero # of DTCs or MIL commanded on in any response message | T | Check V4.4
Document | 5-10079 | There must be a protocol check at the start of the Dynamic Tests 10.1. Test 10.3 refers to 10.1, but this does not currently exist in the 4.2 document. | KStofflet | 2024-09-19 | 2024-10-04 |  | NEED DOC. UPDATE | The software already does this. | T
Bug Fix | 5-10077 | Test 10.10 Still getting 'Response exceeded buffer size' messages from $19 $1A $93, $19 $56 $33 $0E. | joseph.manoni@mercedes-benz.com | 2024-09-05 | 2024-10-04 |  |  | Need to dynamically allocate memory for $19 $1A $91, $19 $1A $93, and $19 $56 $33 $0E. Temporary solution in V04.04.00, dated 11/13/2024; Need to dynamically allocate memory in a later release. | PTI | Temporary solution to hardcode 4K buffers in V04.04.00. NEED TO DYNAMICALLY ALLOCATE MEMORY IN A LATER RELEASE.
Add Feature | 5-10073 | Add ZEV Fault Insertion tests. | J1699 TF | 2024-08-28 | 2024-10-04 |  |  |  | T
Add Feature | 5-10072 | Support multiple edge nodes on DoIP. | AZettel | 2024-08-28 | 2024-10-04 |  |  |  | T
Bug Fix | 5-10065 | Support non-OBD II Compliance Types. | J1699 | 2024-07-24 | 2024-10-04 |  | NEED DOC. UPDATE |  | T
Add Feature | 5-10061 | Test 5.10 should not fail if misfire count ($F502 & $F503) is greater than 0. | joseph.manoni@mercedes-benz.com | 2024-06-11 | 2024-07-12 | 04.00.00 | 8/28/2024 NEED DOC. UPDATE | Added in V04.00.00, dated 8/28/2024. | TI
Add Feature | 5-10059 | J1979-2 indicates that the F4xx, F5xx and F7xx ranges are linked using FxE0 Data D bit 0, but the latest J1979-DA indicates they are not. J1699-5 follows J1979-DA. Are both options allowed? If not, will J1979-2 be updated to match J1979-DA? | Christopher.Oberroithmair@bmw.de | 2024-06-06 | 2024-07-12 | 04.00.00 | 8/28/2024 NEED DOC. UPDATE | 6/10/2024 - Small Group Decision: Linking will PASS thru 2026, 2027 and beyond this will FAIL. Added in V04.00.00, dated 8/28/2024. | TI
Add Feature | 5-10058 | Test 5.16 FAIL/WARN for 0's in F841, F842, F845, F846, F852, F854, F855, F867, F868, F869, F86A, F86B, F86C, F86D, F86E, F86F, F870, F871, F872, F873, F874, F875, F876, F81D, F822, F879, and F882. | John Bowman/Shikha Rathi | 2024-05-29 | 2024-07-12 | 04.00.00 | 8/28/2024 NEED DOC. UPDATE | WAITING FOR TF DECISION Added in V04.00.00, dated 8/28/2024. | TI
Add Feature | 5-10055 | NRCs allowed may change based on powertrain or Compliance Type. | J1699 TF | 2024-05-17 | 2024-05-17 |  | NEED DOC. UPDATE |  | T
Add Feature | 5-10053 | Allow NRC $31 when an ECU does not support a physically addressed SID $14 request. | pweber@na.honda.com | 2024-05-17 | 2024-05-17 | 04.00.00 | 8/28/2024 NEED DOC. UPDATE | Functional and Physical Request: No Response, Positive Response, or Negative Response are valid. Added in V04.00.00, dated 8/28/2024. | TI | (3.4.1) For vehicles using SAE J1979-2, except as provided in sections (g)(3.4.1)(A) and (g)(3.4.1)(B), the OBD II system shall respond to functional (i.e., broadcast) and physical (i.e., point-to-point) request messages from a scan tool in accordance with SAE J1979-2 specifications. (A) The OBD II system may respond to physical Service $14 (i.e., clear/reset emission-related diagnostic information) request messages from a scan tool. CARB REGS: (B) The OBD II system may respond to functional Service $19 subfunction $56 (i.e., “Request DTCs for a ReadinessGroup”) and Service $19 subfunction $1A (i.e., “Request supported DTCExtendedRecord
Add Feature | 5-10052 | What about NRCs that are not identified in Table B, are they allowed? For example SID $22 DIDs F400-F5FF, there is no indication that NRC $21 is not allowed. | shikha.rathi@volvo.com | 2024-05-15 | 2024-05-17 |  | NEED DOC. UPDATE | 5/17/2024 - Original intent was that any NRC not listed would be deemed a FAILURE. Task Force to investigate and make a decision. | T
Add Feature | 5-10021 | Support SMAD (INF $92-$93) in Mfg. Specific Drive Cycle. | J1699-5 V3.3 | 2024-03-25 | 2024-05-17 |  | NEED DOC. UPDATE |  | T
Add Feature | 5-10020 | Allow NRC $22 (Conditions Not Correct) for SID $22 under EOBD. | shikha.rathi@volvo.com | 2024-01-24 |  |  | NEED DOC. UPDATE | 2/26/2024 - Consulting with J1979. 3/1/2024 - NRC $22 (Conditions Not Correct) is allowed for SID $22 in US, but is allowed in EU. Implementataion must wait until after US OBD is fully implemented. | T
Add Feature | 5-10019 | Don't fail vehicles that do not support cylinders 9-16 and do not support SID $22 $F503 and $F505. Don't fail if MISx_CUR_DCY is non-zero. | J1699-5 V3.3 | 2024-01-24 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | 12/8/2023 - TF to review. 3/1/2024 - Don't fail if DID is not supported. Don't fail if MISx_CUR_DCY is non-zero (per V3.6 J1699-5). Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10018 | Test 5.5 / Test 5.13 F6xx Validation; Check for supporting what you say you support and verify response size… no test result validation. | J1699-5 V3.3 | 2024-01-24 | 2024-03-01 |  | NEED DOC. UPDATE | UDS does not repeat Monitor ID in Test Results, so size will be different than in J1699-3. | T
Bug Fix | 5-10014 | Test 5.6 is failing all ECUs if they do not support EGS, CV, EGR, CSER. | shikha.rathi@volvo.com | 2023-10-11 | 2023-12-08 | 02.06.01 | 11/8/2023 NEED DOC. UPDATE | Fixed in V02.06.01, dated 11/8/2023 | TI
Investigate | 5-10013 | Reverse Order test fails on V02.06.00, but works on V02.03.00. | shikha.rathi@volvo.com | 2023-09-27 | 2023-09-29 |  |  |  | T
Add Feature | 5-10011 | Test 5.11 of J1699-5, FreezeFrame data shall be requested SERVICE $19 SUBSERVICE $04. The SW actually requests SERVICE $19 SUBSERVICE $03 instead. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 11/8/2023 NEED DOC. UPDATE | 9/29/2023 - TF to remove test. Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 3-1101 | Add more detail to explaination of "Protocol determination unsuccesful". | J1699-5 | 2024-09-09 | 2024-10-04 |  |  | Wanted to add "No valid response received on any protocol", but there are a lot of other reasons this could fail… need to look into this further. | T
Add Feature | 3-1080 | Test 5.17 fails with "Supports INF $7A (Must not support INF higher than $78)". Need to support more INFs. | theikkin@volvocars.com | 2024-02-12 |  | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 3-1079 | Test 5.17 and Test 9.24 must also check INFs $16-$29 are checked for max. value or "not available". | extern.oliver.schiemann@volkswagen.de | 2024-02-02 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 3-1075 | SID $09 INF $47 should only apply to PHEV/EV. | john.v.bowman@gm.com | 2024-01-29 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 3-1072 | Test 5.17, INFs $52-$5B should change from a FAILURE to a WARNING. | Task Force | 2023-12-09 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 3-1071 | Test 5.17, INF $51 applies to S/S only. | Task Force | 2023-12-09 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 3-1070 | Test 5.17, INFs $48, $49, and $50 apply to PHEV only. | Task Force | 2023-12-09 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 3-1069 | Test 5.17.85, Evaluation criteria is changing to != 0 | Task Force | 2023-12-09 | 2024-03-01 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 3-1067 | Test 5.17, Failure: ECU 18DAF110 INF $42 IEFC-A must return a value of greater than 1. The problem begins when the Clear DTC command included in Test 5.9 resets the active bin information (INF $42 - Engine Idle Fuel Consumption (Active) = 0.0L). In the attached log file, this Clear DTC command occurs approximately 260s prior to INF $42 being requested. Due to the fact, that INF $42 is measured in 0.5L increments and it is not realistic to consume 0.5L of fuel that quickly, a value of 0.0L is reported in Test5.17 and the failure is registered. | jacob.rauser@volvo.com | 2023-11-30 | 2023-12-08 | 03.05.00 | 4/25/2024 NEED DOC. UPDATE | 12/8/2023 - TF agrees to remove value check. Added in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 3-1056 | Test 5.9, Not all ECUs respond to SID $04, but no error is flagged. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-06-07 | 2023-07-14 |  | NEED DOC. UPDATE | Section 5.9.1 is clear that all OBD ECUs must respond negatively, if one does. Code is currently test only ECUs that respond. Section 5.3 is not clear on who must reply for ISO 15765 (do we want logic similar to 5.9.1). Code is currently test only ECUs that respond. | T
Add Feature | 3-1050 | There is a large time gap between request and receive. | brianp@dashlogic.com | 2023-03-23 | 2023-03-23 |  |  |  | T
Add Feature | 3-1046 | Define a new test for a group PID requests containing a known unsupported PID. | Task Force | 2023-01-13 | 2023-01-13 |  | NEED DOC. UPDATE |  | T
Add Feature | 3-1014 | Discuss support for CNG engines in J1699. | yong.yu@arb.ca.gov |  |  |  | NEED DOC. UPDATE |  | T
Bug Fix | 3-1011 | Test 9.23 seems to abort after choosing not to continue with Dynamic Tests. | brandon.baumgartner@stellantis.com |  |  |  |  | It is unclear what is going on here. | T
Bug Fix | 3-1010 | Test 9.19: 407 second gap in network activity resulting in false failure. | GyuMan.Hwang@hyundai-kefico.com |  |  |  |  | It is unclear what is going on here. 3/16/22 - This is a sumulation on a HIL, with bad data. J2534 firmware upated and will retest with appropriate data. THIS DOES NOT APPEAR TO BE A J1699-3 SOFTWARE ISSUE. | T
Items on HOLD
Closed Items
Document | 5-10084 | The document is not clear... are NRC allowed for Functional Requests? | john.v.bowman@gm.com | 2024-09-19 | 2024-10-04 |  | 2024-10-25 | Software currenlty fails if there is an NRC to a Functional Request. Document updated (V4.4), see #5-10090. | T
Bug Fix | 5-10083 | Test 5.6 should FAIL if DID $F401 is supported. | john.v.bowman@gm.com | 2024-09-19 | 2024-10-04 | 04.04.00 | 2024-11-13 | Currently, the software FAILs if $F401 is not supported. Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10081 | Test 5.4 The evaluation of SID $22 DID $F501 depends upon the DIDSupported DIDs, but they not currently being requested. | john.v.bowman@gm.com | 2024-09-19 | 2024-10-04 | 04.04.00 | 2024-11-13 | There is no DIDSupported DID request up to this point, which must be evaluated. VerifyMILData() expects the $F500 DIDSupported DID request has already happened and only checks to see if 'at least one ECU supports $F501'. This causes all of the evaluations of DID $F501 to be skipped. Fixed call to DIDSupported DID in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10080 | Test 5.4 requests SID $01 PID $00, but SID $01 PID $01 is required. | john.v.bowman@gm.com | 2024-09-19 | 2024-10-04 | 04.04.00 | 2024-11-13 | Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10078 | Remove protocol check from Tests 5.8, 6.2, 7.2, 8.2, 9.2, 9.9, 9.13, 9.17, and 9.21. | john.v.bowman@gm.com | 2024-09-19 | 2024-10-04 | 04.04.00 | 2024-11-13 | Protocol check shoul only be in Test 5.2, 10.1, 11.4, and 12.1. Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10076 | Test 5.6 No FAILURE is flagged if an ECU indicates support for the next DIDSupported DID, but that DIDSupported DID is not supported. | joseph.manoni@mercedes-benz.com | 2024-09-05 | 2024-10-04 | 04.04.00 | 2024-11-13 | Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10075 | Test 5.6 Receiving an NRC from a bad ECU prevents subsequent group requests for good ECUs from being made. This causes false failures in good ECUs. | joseph.manoni@mercedes-benz.com | 2024-09-05 | 2024-10-04 | 04.04.00 | 2024-11-13 | Issue with looping logic in RequestGroupPIDSupportData(). Lower priority, issue is only visible when there is an ECU failure. Fixed in V04.04.00, dated 11/13/2024. | PTI
Add Feature | 5-10074 | Prompt Q02 Add "ICE" to the #1 and #2 selections. | J1699-5 | 2024-09-05 | 2024-10-04 | 04.04.00 | 2024-11-13 | Change the tex to be: “1. Run ICE Static Tests contained in Sections 5 through 9.” “2. Run ICE Dynamic Tests contained in Section 10 through 11.” Added in V04.04.00, dated 11/13/2024. | PTI
Add Feature | 5-10071 | Correct $F41C range check for greater than or equal to instead of just greater than MAX_OBD_TYPES. | KStofflet | 2024-08-28 | 2024-10-04 | 04.00.00 | 2024-08-28 | Fixed in V04.00.00, dated 8/28/2024. | TI
Add Feature | 5-10070 | Incorrect pointer assignment which could prevent evaluation of Protocol ID response. | KStofflet | 2024-08-28 | 2024-10-04 | 04.00.00 | 2024-08-28 | Fixed in V04.00.00, dated 8/28/2024. | TI
Add Feature | 5-10069 | Test category selection prompts updated to match document. | J1699-5 V4.1 | 2024-08-28 | 2024-10-04 | 04.00.00 | 2024-08-28 | Added in V04.00.00, dated 8/28/2024. | TI
Add Feature | 5-10068 | Test 5.16 Fail if $F878 Engine Rated Power and Engine Rated Speed are set to 0. | J1699-5 V4.1 | 2024-08-27 | 2024-10-04 | 04.04.00 | 2024-11-13 | Added in V04.04.00, dated 11/13/2024. | T
Bug Fix | 5-10067 | Test 10.3 is failing without a FAILURE being logged. The call chain is StartLog() -> RequestIDSupportData() -> RequestSID(), where we get an NRC for SID $22 DID $F8A0, because it is not supported. This appears to be due to getting an NRC $31 to the next unsupported INF, which sets 'bTestFailed = TRUE;' in RequestIDSupportData() without logging an error (because gstResponse[EcuIdx].INFSize == 0). We should flag errors on NRC to Functionally addressed requests, but allow them on Physically addressed requests. | Navyasree.Kanjarla@in.bosch.com | 2024-07-30 | 2024-10-04 | 04.04.00 | 2024-11-13 | Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10066 | The function DisplayPid01() is using data from DID $F501 not $F401. The code uses the line: pPid = &gstResponse[EcuIdx].PIDF501; | Navyasree.Kanjarla@in.bosch.com | 2024-07-30 | 2024-10-04 | 04.00.00 | 2024-08-28 | Fixed in V04.00.00, dated 8/28/2024. | TI
Bug Fix | 5-10064 | Test 5.16 should not FAIL/WARN if $F808/$F80B is not supported. | John Bowman | 2024-07-24 | 2024-10-04 | 04.00.00 | 2024-08-28 | Fixed in V04.00.00, dated 8/28/2024. | TI
Add Feature | 5-10063 | Test 10.10 needs to clearly identify what to do with a broadcast request for a Readiness Group that is not supported by the vehicle. | shikha.rathi@volvo.com | 2024-07-10 | 2024-07-12 | 04.04.00 | 2024-11-13 | S/W currently fails vehicle. Functional and Physical Requestto 19 56 or 19 1A: No Response, Positive Response, or Negative Response are valid. J1699-5 Doc V4.1 addresses this. Added in V04.04.00, dated 11/13/2024. | PTI | (3.4.1) For vehicles using SAE J1979-2, except as provided in sections (g)(3.4.1)(A) and (g)(3.4.1)(B), the OBD II system shall respond to functional (i.e., broadcast) and physical (i.e., point-to-point) request messages from a scan tool in accordance with SAE J1979-2 specifications. (A) The OBD II system may respond to physical Service $14 (i.e., clear/reset emission-related diagnostic information) request messages from a scan tool. CARB REGS: (B) The OBD II system may respond to functional Service $19 subfunction $56 (i.e., “Request DTCs for a ReadinessGroup”) and Service $19 subfunction $1A (i.e., “Request supported DTCExtendedRecord
Bug Fix | 5-10062 | Test 10.10 $19 $1A $91, $19 $1A $93, and $19 $56 $33 $0E all produce a 'response data exceeded buffer size' error. The buffer currently holds 47 (MAX_DTCIUMPR_COUNT, and MAX_DTCIMR_COUNT), but need to be 256 each. | shikha.rathi@volvo.com | 2024-07-10 | 2024-07-12 | 04.00.00 | 2024-08-28 | Increased buffer size but did not fix in V04.00.00, dated 8/28/2024. Need to dynamically allocate memory. See #5-10077. | TI
Add Feature | 5-10060 | Test 6.4 (in log; 6.3 in doc) FAILED for a Type A (first trip) DTC, but it should not. | John Bowman/Shikha Rathi | 2024-06-10 | 2024-07-12 | 04.04.00 | 2024-11-13 | The J1699-5 document says to repeat test 5.12, but the evaluation criteria of 5.12 says 'fail if DTC set'. The intent is to use the Rx/Tx messages from Test 5.12 but different evaluation criteria, which is not documented in Test 6.3. This goes for Test 6.x, 7.x, 8.x, and 9.x as they have the same “repeat 5.x” text. Fixed in J1699-5 V4.1. Added in V04.00.00, dated 8/28/2024, but it is not fixed. Code is checking MIL, but that DID has not been requested after the DTC is set. Consider changing the order of VerifyConfirmedDTCData() and VerifyMILData() in Test6_PendingDTC.c for Test 6.4. CAUTION: VerifyMILData() expects the DIDSupported DID requests for DID $F501... SEE #5-10081. Fixed in V04.04.00, dated 11/13/2024. | PTI
Bug Fix | 5-10057 | Test 5.16 Fail/Warn messages for INF $F854 AT2_TIME_S reports "AT1_TIME-S", AT2_DT-S reports "AT1DT-S", and AT2_DT-L reports "AT1DT-L". | shikha.rathi@volvo.com | 2024-05-17 | 2024-07-12 | 04.00.00 | 2024-08-28 | Typo in error message for number and "_"; lines 10161, 10182, 10212, 10233 in VerifyINFSupportAndData.c. Fixed in V04.00.00, dated 8/28/2024. | TI
Bug Fix | 5-10056 | Test 5.16 Fail/Warn messages say "INF $F841 ERT-A must return a value of greater than 1 sec" but should say "INF $F841 EOE-A must…" | shikha.rathi@volvo.com | 2024-05-17 | 2024-07-12 | 04.00.00 | 2024-08-28 | Typo in error message. Fixed in V04.00.00, dated 8/28/2024. | TI
Add Feature | 5-10054 | DID $F4CA has been deleted. If supported, do not check size or attempt to decode. | J1699 TF | 2024-05-17 | 2024-05-17 | No Change | 2024-08-28 | Code does not decode. | TI
Add Feature | 5-10051 | Need to confirm that SID $22 DIDs: $F4AF required for "OBD II, HD OBD – 2024MY+" $F4D3 required for "HD OBD – 2024MY+ Fail" $F4AD $F4B0 How is "D, HD OBD 2024MY+, if equipped" determined for SID $22 DID $F4D7? Supported column does not always indicate "FAIL/WARN" (e.g., $F4AE, $F4AF, $F4B0, etc.) | shikha.rathi@volvo.com pweber@na.honda.com | 2024-05-15 | 2024-05-17 | 04.00.00 | 2024-08-28 | 5/17/2024 - Task Force to investigate and make a decision. V4.0 of doc says do not warn/fail for no support. Added in V04.00.00, dated 8/28/2024. | TI
Bug Fix | 5-10050 | Add missing newline to end of failure message for DID-Support DID indicating no DIDs supported. | J1699-5 | 2024-05-08 | 2024-05-17 | 03.05.01 | 2024-05-13 | Added in V03.05.01, dated 5/13/2024. | TI
Bug Fix | 5-10049 | The response for SID $22 DID F810 is not evaluated being evaluated. | J1699-5 | 2024-05-08 | 2024-05-17 | 03.05.01 | 2024-05-13 | Added in V03.05.01, dated 5/13/2024. | TI
Bug Fix | 5-10048 | Test 5.16 - Storing/evaluating of INFs over $7F may cause the application to crash. | shikha.rathi@volvo.com | 2024-05-08 | 2024-05-17 | 03.05.01 | 2024-05-13 | Added in V03.05.01, dated 5/13/2024. | TI
Add Feature | 5-10047 | Change INF $F86D-76 verification to fail if Lifetime data is zero. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10046 | Change INF $F867-6C verification to fail if Stored data is zero. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10045 | Change INF $F861-66 verification to fail if Active data is not zero after clear codes command. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10044 | Change INF $F851-5B verification to fail if Stored and Lifetime counters are zero. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10043 | Change INF $F848-50 verification to fail if Stored and Lifetime counters are zero for PHEV and warn if Active and Lifetime counters are both zero for PHEV. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10042 | Change INF $F847 verification to fail if Total and Idle PSA time Lifetime counters are zero for P/HEV and warn if Urban PSA Active and Lifetime counters are zero for P/HEV. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10041 | Change INF $F846 verification to fail if Idle run time lifetime counter are zero and warn if Engine FC and Idle FC, PKE, and Urban Speed Run counters are zero. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10040 | Change INF $F845 verification to fail if ERT and EOE lifetime counters are zero for CONV and S/S or warn if P/HEV, and warn if DT and FC lifetime counter are zero. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10039 | Change INF $F842 verification to fail if Idle Active counters (except Idle FC, see 3-1067) are zero and warn if Engine FC, Idle FC, Urban Speed Run, and PKE counters are zero. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10038 | Change INF $F841 verification to fail if ERT and EOE Active counters are zero for CONV and S/S or warn if P/HEV, and warn if DT and FC Active counter are zero. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10037 | Change INF $F81D-1F,21-2A evaluation to warn if Recent and Lifetime values are equal or zero and warn if it is supported but all timers are "not available". | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10036 | Change INF $F81A-1C evaluation to warn if Recent and Lifetime values are equal or zero for PHEV. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10035 | Change INF $F819 evaluation to fail if Recent and Lifetime values are equal or zero for Total and Idle PSA and warn if Recent and Lifetime values are zero or Equal for City PSA. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10034 | Change INF $F818 evaluation to fail if Recent and Lifetime values are equal or zero for CONV and S/S or warn for HEV and PHEV. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10033 | Change INF $F817 evaluation to warn if Recent and Lifetime DT values are zero OR equal, warn if Recent and Lifetime FC values are zero for HEV or PHEV, fail if Recent and Lifetime FC values are equal for CONV and S/S, and fail if Fuel Consumed Bytes not supported for EOBD. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10032 | Added evaluation for PIDs $F4CF, D3, and D7. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10031 | Added required support evaluate for INF $F883 and $F884. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10030 | Added function to evaluate INF $F82A. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 5-10029 | Fix formatting of printing of values in PID $F4C9 and $F4CB. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 5-10028 | Fix PID display for $F505 (it used to mistakely show $F504). | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 5-10027 | Fix MDDC check for PID $F4A2 (was incorrectly compared to gstUserInput.eComplianceType, now compared to gstUserInput.eVehicleType). | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 5-10026 | Fix the misspelling in RequestGrouPIDSupportData to RequestGroupPIDSupportData (found while working on 5-10017). | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 5-10025 | Comment out MID tests (and VerifyVehicleState tests when the rest of the test section is not performed). | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 5-10024 | Clean up defunct, commented-out code and change Physically/Functionally addressed coding for new standard. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 5-10023 | Add size checks for PID $F4A7,A8,AA,AC-B1,C3,C7,C9,CB,CF,D3,D7. | J1699-5 V3.5 | 2024-04-25 | 2024-05-17 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10022 | Add ZEV DID Validation Tests. | J1699-5 | 2024-03-25 | 2024-05-17 | 04.04.00 | 2024-11-13 | Fixed in V04.04.00, dated 11/13/2024. | PTI
Add Feature | 5-10017 | PID Supported PIDs F4E0 and F5E0 should both have bit 0 set to 0. | J1699-5 V3.3 | 2024-01-24 | 2024-03-01 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10016 | Add definitions for EnergyType and FuelType and remove EngineType and gbDiesel to match document. | Task Force / V2.6 Document | 2023-10-31 | 2023-12-08 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Add Feature | 5-10015 | Change Europe and China compliance types to better match document. | Task Force / V2.6 Document | 2023-10-31 | 2023-12-08 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10012 | Byte #4 in a Freeze Frame Response should be $FF, but J1699-5 expects $04. Test 5.14 / Test 8.3 / Test 9.3 with a false WARNING. Test 6.3 ends up in an infinite loop, based upon the same issue. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10010 | Test 5.10 evaluation of PID $F501 issues with engine running. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10009 | When testing on a light duty car, J1699-5 requires heavy duty PIDs to be present. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10008 | Test 5.8 ends when there is no response to PID $F40D on 29-bit, but a link monitor shows there was a response. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-06 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 5-10007 | Allow subtest to continue after failure in DID-Support DID check. | kstofflet@engenius.com | 2023-08-03 | 2023-09-29 | 02.06.00 | 2023-08-07 | Fixed in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10006 | Remove Tester Present option. | Small Group | 2023-08-03 | 2023-09-29 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10005 | Implement J1699-5 specified Dynamic Test (IUMPR equivalent). | Task Force / V2.6 Document | 2023-07-31 | 2023-09-29 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Add Feature | 5-10004 | Support the MIL Exclusion file, like J1699-3 does. | john.v.bowman@gm.com | 2023-07-14 | 2023-09-29 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10003 | Test 5.5, 5.6 FAILs ECUs because physical requests are being made to ECUs that indicate they do not support the parameter. |  | 2023-06-01 | 2023-07-14 | 02.06.00 | 2023-08-07 | Task Force to clarify NRCs allowed. Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10002 | Test 5.8 communication seems to stop after protocol check (no further response received). |  | 2023-06-01 | 2023-07-14 | 02.06.00 | 2023-08-07 | May be related to NRC issue. Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 5-10001 | Add support for ETHERNET_NDIS. | Task Force / V2.5 Document | 2023-05-18 | 2023-07-14 | 04.00.00 | 2024-08-28 | Added in V04.00.00, dated 8/28/2024. | TI
Bug Fix | 5-10000 | Protocol determination uses SID $01 PID $00, but it should use SID $22 PID $F810. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2022-06-17 | 2022-07-22 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1090 | Test 9.22 INF $18 - Remove EOE-R, EOE-L, PKE-R, and PKE-L checks for '>0' or comparisons to 5.17 data. | J1699-3 V17.6 | 2024-07-29 | 2024-10-04 | 04.00.00 | 2024-08-28 | Added in V04.00.00, dated 8/28/2024. | TI
Add Feature | 3-1089 | VerifyInf66_6C_72_76Data must collect the sum of [bin2] through [bin14] and compare to [bin1] for INF $66, $6C, $72, $76. | J1699-3 V17.7 | 2024-07-29 | 2024-10-04 | 04.00.00 | 2024-08-28 | Added in V04.00.00, dated 8/28/2024. | TI
Add Feature | 3-1088 | VerifyInf65_6B_71_75Data must collect the sum of [bin2] through [bin14] and compare to [bin1] for INF $65, $6B, $71, $75. | J1699-3 V17.7 | 2024-07-29 | 2024-10-04 | 04.00.00 | 2024-08-28 | Added in V04.00.00, dated 8/28/2024. | TI
Add Feature | 3-1087 | VerifyInf64_6A_70_74Data must collect the sum of [bin2] through [bin14] and compare to [bin1] for INF $74. | J1699-3 V17.7 | 2024-07-29 | 2024-10-04 | 04.00.00 | 2024-08-28 | Added in V04.00.00, dated 8/28/2024. | TI
Add Feature | 3-1086 | VerifyInf63_69_6F_73Data must collect the sum of [bin2] through [bin14] and compare to [bin1] for INF $73. | J1699-3 V17.7 | 2024-07-29 | 2024-10-04 | 04.00.00 | 2024-08-28 | Added in V04.00.00, dated 8/28/2024. | TI
Bug Fix | 3-1078 | Q10 Prompt needs to accept more than one digit. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2024-02-02 |  | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Add Feature | 3-1077 | Q03 Prompt needs to accept >2025 MY. | extern.oliver.schiemann@volkswagen.de | 2024-02-02 | 2024-03-01 | 03.05.00 | 2024-04-25 | Added in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 3-1076 | SID $01 PID $A3 has evaluation criteria in code, but there is no requirement in the document. | Gabor.Tarnai@vitesco.com | 2024-02-02 | 2024-03-01 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 3-1066 | Using J1699_CONFIG.INI, Test 5.17 is producing "FAILURE: INF $6 (CVN) supported by less than the expected number of ECUs ( 1 support, 1 expected)!", but it seems like it shouldn't. | topi.heikkinen@volvocars.com | 2023-10-18 | 2023-12-08 | 03.05.00 | 2024-04-25 | Fixed in V03.05.00, dated 4/25/2024. | TI
Bug Fix | 3-1065 | False fail for unsupported signals in tracking INFs like $17 in EU. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-09-27 | 2023-09-29 | 02.06.01 | 2023-11-08 | Since EU does not require “recent” values in the INFs, an ECU may report 0xFFFF as indication of unsupported values. We already had this problem tracked as issue 290. Back in those days we had solved this very issue in Version 16.07.00. Now, in the actual version(s) it shows up again. Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 3-1063 | Test 5.17 for SID $09 INF $77 should WARN for 2022-2023 and FAIL for 2024, but currently FAILs . | shikha.rathi@volvo.com | 2023-08-28 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Add Feature | 3-1062 | SID $09 INF $78 should only apply to diesel MD, MDDC, and HD. | john.v.bowman@gm.com | 2023-08-04 | 2023-09-29 | 02.06.01 | 2023-11-08 | Fixed in V02.06.01, dated 11/8/2023 | TI
Bug Fix | 3-1060 | Fix bug that would cause crash if current and previous vehicle test type did not match. | kstofflet@engenius.com | 2023-07-14 | 2023-09-29 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1057 | Test 11.2, ESC key not functioning correctly, it causes test to FAIL instead of EXIT. | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-07-13 | 2023-07-14 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1054 | Correct EOBD Code Clear to allow a mixed response only on Key On Engine Running. | Task Force | 2023-05-19 | 2023-05-19 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1053 | Application is locking up at splash screen with Windows 11 Pro, Ver 22H2 OSbuild 22621.1702. | RobertT@NRD.NISSAN-USA.COM | 2023-05-18 | 2023-07-14 | 02.06.00 | 2023-08-07 | Fixed in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1052 | In Test 11.2, displays IUMPR incorrect initial counters for ECUs that are not on the 'first page'. | Peter.Crawford@kiageorgia.com | 2023-05-04 | 2023-05-19 | 02.06.00 | 2023-08-07 | Fixed in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1051 | In Test 11.2, do not display IUMPR info for ECUs that do not support IUMPR but do support I/M Readiness. Currently the counter names and zeros are displayed. | Peter.Crawford@kiageorgia.com | 2023-05-04 | 2023-05-19 | 02.06.00 | 2023-08-07 | Fixed in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1049 | On partially compliant J2534 Interfaces, errors are logged when attempting to clear filters on a channel that was never opened. | brianp@dashlogic.com | 2023-03-23 | 2023-03-23 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1048 | SID $09 INF $77 should not have a phase in period. | Task Force | 2023-03-23 | 2023-03-23 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1047 | Update the wording in Test 6.1 that requests a two trip DTC. | john.v.bowman@gm.com | 2021-08-08 | 2023-03-24 | 02.06.00 | 2023-08-07 | Also change "disconnect sensor" to "induce fault" throughtout code. Added in V02.06.00, dated 8/7/2023. | TI
Bug Fix | 3-1041 | Fix display resolution loss in calculation of PID $85 and $96 from using TempData_long instead of TempData_float (display only, no evaluation of these PIDS). | kstofflet@engenius.com | 2023-02-13 | 2023-03-24 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1040 | Fix display resolution loss in calculation of PID $85 and $96 from using TempData_long instead of TempData_float (display only, no evaluation of these PIDS). | kstofflet@engenius.com | 2023-02-13 | 2023-03-24 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1039 | Test 5.6, PID $A1 has an incorrect data transformation. It lists NOXC12_SUP but should be NOXC12_SUP; NOXC12_SUP should be NOXC21_SUP; NOXC11_DAT_AVAIL is listed for NOXC12, NOXC21, and NOXC22; Also the data evauluation for NOXC11 and NOXC12 is comparing TempData_float instead of TempData_long. | shikha.rathi@volvo.com | 2023-02-13 | 2023-03-24 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1035 | Split MD and LD in the Vehicle Type prompt, including all tests that use this logic. | Task Force | 2023-01-13 | 2023-01-13 | 02.06.00 | 2023-08-07 | Added in V02.06.00, dated 8/7/2023. | TI
Add Feature | 3-1034 | Clarify wording in the phase-in WARNING for new INFs. | Task Force | 2023-01-13 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1033 | Clarify wording in Q03 to indicate it is VIN Model Year. | Task Force | 2023-01-13 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1031 | Test 11.2 waiting for Bank2 to complete, when vehicle only has Bank1. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-22 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1030 | Test 9.19 and 11.2 crash with China6 selected. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-22 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1029 | Test11.2 with implausible data for initial IUMPRs | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-19 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1028 | Extra space added between "*" and "T" (+000000ms RESULTS: **** Test 5.1 PASSED ****), which breaks tools. It needs to be added back. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-19 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1027 | False failure in Test 5.17 for missing INF $78. This should be for HD and MD only, not LD. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-19 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1025 | In the Dynamic Test, after logging the meta information, it starts somewhere within Test 10.3. So, Tests 10.1 and 10.2 are missing completely, the same is true for the first part of Test 10.3. | hans.joerg.brinksmeyer@volkswagen.de | 2022-12-19 | 2023-01-13 | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Bug Fix | 3-1024 | Test 5.18 incorrectly flags the response to a SID $01 PID $E0, $C0 group request as a failure if $E0 is not supported. | Jianwei_Zhong@PATAC.com.cn | 2022-11-15 |  | 02.03.00 | 2023-03-14 | Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1021 | Fix confusing error message when ECU didn't respond or responded with incorrect ID to PIDSupported PID. | Bosch |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1020 | China6 does not require all or nothing when clearing codes like OBD II does (e.g., during KOER)? | Mitchell.Olson@na.mitsubishi-motors.com |  |  | 02.03.00 | 2023-03-14 | Looks like this is not a requirement for China6; 3/11/22 TF - M. Laleman confirmed this. Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1019 | INF $78 RPM range should be up to 5000 for all vehicles. | J1699-3 TF |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1018 | In Test 5.17, remove the evaluation criteria for checking the Stored parameter, but leave the criteria for doing the length check in infotypes $43, $44, $67, $68, $69 and $6A. | J1699-3 TF |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Bug Fix | 3-1016 | Tests 11.5 and 11.8 have a mismatch between the Mode $01 PID $01 data actually reported by the ECU and the new “information view” onto the readiness data. | hans.joerg.brinksmeyer@volkswagen.de |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1013 | Test 5.17 GHG INF requirements apply to all HD Vehicles. Should this also consider the type of Regulatory/Engine/Powertrain? | john.v.bowman@gm.com |  |  | 02.03.00 | 2023-03-14 | John has a table to try an identify valid combinations. 1/14/22 TF to set up small group meeting to define requirements. Fixed in V02.03.00, dated 3/14/2023. | TI
Add Feature | 3-1012 | Proposal to add a prompt for Engine Certification Year and suggestions on how it a VIN should be evaluated. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Bug Fix | 3-1009 | Test 5.17 request the next unsupported INFSupported INF, but there is no longer a requirement to do this. This code should be removed from the software | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1006 | Test 5.17 Nox BINs 2-17 compare to BIN 1 must be +-1% to allow for allow for resolution and error compounding. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1005 | SID $09 INF $6D, $6E, $6F, and $70 fail if value == 0, but 0 is valid value. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1004 | Test 5.17 does not support INF greater than $29. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Add Feature | 3-1003 | SID $09 INF $78 needs to allow Diesels to have a range of x > 0 | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | T
Bug Fix | 3-1002 | Error if SID $09 INF $6D has a value of 0. Should test fail ONLY if Lifetime < Active; If Lifetime = Active = 0 then it should pass. | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | T
Bug Fix | 3-1001 | Test 7.5, 8.5, and 9.5 produce errors regarding PID$C0 Group request mismatch. Test 5.18 produces errors regarding PID$C3 support | john.v.bowman@gm.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | T
Bug Fix | 3-1000 | Reverse order PID request is failing when ECU supports less than 6 PIDs. | KiWang.Kim@hyundai-kefico.com |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | T
Add Feature | 3-220 | The Burst Test (Test 5.20) fails due to PC factors outside of the control of the J1699-3 software (e.g., virus scanning software, Windows, etc.). The evaluation criteria should be changed to examine only the ECU response times over say 200 requests. This would eliminate the impact of PC delays because we would not be counting the number of message round-trips for a given period of time. Instead, we would only be examining the ECU response times as derived from the Pass-Thru Device message data, which would not be impacted by PC delays. | Hans.Joerg.Brinksmeyer@Volkswagen.de |  |  | 1.00.00 Beta | 2022-04-15 | Included in in V1.00.00, dated 4/15/2022. | TI
Discussion | Not Assigned | What is the expected response to J1979 Classic SID requests… is it no response? The J1699-5 document should detail this in the NRC table. | joseph.manoni@mercedes-benz.com | 2024-06-11 | 2024-07-12 | No Change | 2024-06-18 | TF - No response is allowed. The software already supports this, so no change is needed. | T
Discussion | Not Assigned | Can we get rid of the Tester Present option? | Hans.Joerg.Brinksmeyer@Volkswagen.de | 2023-06-07 | 2023-07-14 | Closed | 2023-08-07 | Removed see Issue 5-10006 | T

## J1699-5 Work Schedule
Approximate Release Date | SF # | Description | J1699-5 Status
Mid-Mar., 2023
| 3-1013 | Test 5.17 GHG INF requirements apply to all HD Vehicles. Should also consider the type of Regulatory/Engine/Powertrain. | In J1699-5
| 3-1020 | China6 does not require all or nothing when clearing codes like OBD II does (e.g., during KOER). | In J1699-5
| 3-1024 | Test 5.18 incorrectly flags the response to a SID $01 PID $E0, $C0 group request as a failure if $E0 is not supported. | In J1699-5
| 3-1025 | In the Dynamic Test, after logging the meta information, it starts somewhere within Test 10.3. So, Tests 10.1 and 10.2 are missing completely, the same is true for the first part of Test 10.3. | In J1699-5
| 3-1027 | False failure in Test 5.17 for missing INF $78. This should be for HD and MD only, not LD. | In J1699-5
| 3-1028 | Extra space added between "*" and "T" (+000000ms RESULTS: **** Test 5.1 PASSED ****), which breaks tools. It needs to be added back. | In J1699-5
| 3-1029 | Test 11.2 with implausible data for initial IUMPRs | In J1699-5
| 3-1030 | Test 9.19 and 11.2 crash with China6 selected. | In J1699-5
| 3-1031 | Test 11.2 waiting for Bank2 to complete, when vehicle only has Bank1. | In J1699-5
| 3-1033 | Clarify wording in Q03 to indicate it is VIN Model Year. | In J1699-5
| 3-1034 | Clarify wording in the phase-in WARNING for new INFs. | In J1699-5
| 3-1039 | Test 5.6, PID $A1 has an incorrect data transformation. | In J1699-5
| 3-1040 | Fix display resolution loss in calculation of PID $85 and $96. | In J1699-5
| 3-1041 | Change TEST 11.2 on-screen text from RESERVED to GPF for gasoline vehicles. | In J1699-5
| 5-10000 | Protocol determination uses SID $01 PID $00, but it should use SID $22 PID $F810. | In J1699-5
Early August, 2023
| 3-1035 | Split MD and LD in the Vehicle Type prompt, including all tests that use this logic. | In J1699-5
| 3-1047 | Update the wording in Test 6.1 that requests a two trip DTC. | In J1699-5
| 3-1048 | INF $F877 should not have a phase in period. | In J1699-5
| 3-1049 | On partially compliant J2534 Interfaces, errors are logged when attempting to clear filters on a channel that was never opened. | In J1699-5
| 3-1051 | In Test 11.2, do not display IUMPR info for ECUs that do not support IUMPR but do support I/M Readiness. | In J1699-5
| 3-1052 | In Test 11.2, displays IUMPR incorrect initial counters for ECUs that are not on the 'first page'. | In J1699-5
| 3-1053 | Application is locking up at splash screen with Windows 11 Pro, Ver 22H2 OSbuild 22621.1702. | In J1699-5
| 3-1054 | Correct EOBD Code Clear to allow a mixed response only on Key On Engine Running. | In J1699-5
| 3-1057 | Test 11.2, ESC key not functioning correctly, it causes test to FAIL instead of EXIT. | In J1699-5
| 3-1060 | Fix bug that would cause crash if current and previous vehicle test type did not match. | In J1699-5
| 5-10002 | Test 5.8 communication seems to stop after protocol check (no further response received). | In J1699-5
| 5-10003 | Test 5.5, 5.6 FAILs ECUs because physical requests are being made to ECUs that indicate they do not support the parameter. | In J1699-5
| 5-10004 | Support the MIL Exclusion file, like J1699-3 does. | In J1699-5
| 5-10006 | Remove Tester Present option. | In J1699-5
| 5-10007 | Allow subtest to continue after failure in DID-Support DID check. | In J1699-5
Early Nov., 2023
| 3-1062 | SID $09 INF $78 should only apply to diesel MD, MDDC, and HD. | In J1699-5
| 3-1063 | Test 5.17 for SID $09 INF $77 should WARN for 2022-2023 and FAIL for 2024, but currently FAILs. | In J1699-5
| 3-1065 | False fail for unsupported signals in tracking INFs like $17 in EU. | In J1699-5
| 5-10008 | Test 5.8 ends when there is no response to PID $F40D on 29-bit, but a link monitor shows there was a response. | In J1699-5
| 5-10009 | When testing on a light duty car, J1699-5 requires heavy duty PIDs to be present. | In J1699-5
| 5-10010 | Test 5.10 evaluation of PID $F501 issues with engine running. | In J1699-5
| 5-10011 | Test 5.11 of J1699-5, FreezeFrame data shall be requested a SERVICE $19 SUBSERVICE $04. The SW actually requests SERVICE $19 SUBSERVICE $03 instead. | In J1699-5 |  | NEED DOC
| 5-10012 | Byte #4 in a Freeze Frame Response should be $FF, but J1699-5 expects $04. Test 5.14 / Test 8.3 / Test 9.3 with a false WARNING. Test 6.3 ends up in an infinite loop, based upon the same issue. | In J1699-5
| 5-10014 | Test 5.6 is failing all ECUs if they do not support EGS, CV, EGR, CSER. | In J1699-5 |  | NEED DOC
| 5-10015 | Change Europe and China compliance types to better match document. | In J1699-5
| 5-10016 | Add definitions for EnergyType and FuelType and remove EngineType and gbDiesel to match document. | In J1699-5
mid-April, 2024
| 3-1066 | Using J1699_CONFIG.INI, Test 5.17 is producing "FAILURE: INF $6 (CVN) supported by less than the expected number of ECUs ( 1 support, 1 expected)!" | In J1699-5
| 3-1067 | Test 5.17, Failure: ECU 18DAF110 INF $42 IEFC-A must return a value of greater than 1. | In J1699-5 |  | NEED DOC
| 3-1069 | Test 5.17.85, Evaluation criteria is changing to != 0 | In J1699-5 |  | NEED DOC
| 3-1070 | Test 5.17, INFs $48, $49, and $50 apply to PHEV only. | In J1699-5 |  | NEED DOC
| 3-1071 | Test 5.17, INF $51 applies to S/S only. | In J1699-5 |  | NEED DOC
| 3-1072 | Test 5.17, INFs $52-$5B should change from a FAILURE to a WARNING. | In J1699-5 |  | NEED DOC
| 3-1075 | SID $09 INF $47 should only apply to PHEV/EV. | In J1699-5 |  | NEED DOC
| 3-1076 | SID $01 PID $A3 has evaluation criteria in code, but there is no requirement in the document. | In J1699-5
| 3-1077 | Q03 Prompt needs to accept >2025 MY. | In J1699-5 |  | NEED DOC
| 3-1078 | Q10 Prompt needs to accept more than one digit. | In J1699-5
| 3-1079 | Test 5.17 and Test 9.24 must also check INFs $16-$29 are checked for max. value or "not available". | In J1699-5 |  | NEED DOC
| 3-1080 | Test 5.17 fails with "Supports INF $7A (Must not support INF higher than $78)". Need to support more INFs. | In J1699-5 |  | NEED DOC
| 5-10005 | Implement J1699-5 specified Dynamic Test (IUMPR equivalent). | In J1699-5
| 5-10017 | PID Supported PIDs F4E0 and F5E0 should both have bit 0 set to 0. | In J1699-5
| 5-10019 | Don't fail vehicles that do not support cylinders 9-16 and do not support SID $22 $F503 and $F505. | In J1699-5 |  | NEED DOC
| 5-10023 | Add size checks for PID $F4A7,A8,AA,AC-B1,C3,C7,C9,CB,CF,D3,D7. | In J1699-5
| 5-10024 | Clean up defunct, commented-out code and change Physically/Functionally addressed coding for new standard. | In J1699-5
| 5-10025 | Comment out MID tests (and VerifyVehicleState tests when the rest of the test section is not performed). | In J1699-5
| 5-10026 | Fix the misspelling in RequestGrouPIDSupportData to RequestGroupPIDSupportData (found while working on 5-10017). | In J1699-5
| 5-10027 | Fix MDDC check for PID $F4A2 (was incorrectly compared to gstUserInput.eComplianceType, now compared to gstUserInput.eVehicleType). | In J1699-5
| 5-10028 | Fix PID display for $F505 (it used to mistakely show $F504). | In J1699-5
| 5-10029 | Fix formatting of printing of values in PID $F4C9 and $F4CB. | In J1699-5
| 5-10030 | Added function to evaluate INF $F82A. | In J1699-5
| 5-10031 | Added required support evaluate for INF $F883 and $F884. | In J1699-5
| 5-10032 | Added evaluation for PIDs $F4CF,D3,and D7. | In J1699-5
| 5-10033 | Change INF $F817 evaluation to warn if Recent and Lifetime DT values are zero OR equal, warn if Recent and Lifetime FC values are zero for HEV or PHEV, fail if Recent and Lifetime FC values are equal for CONV and S/S, and fail if Fuel Consumed Bytes not supported for EOBD. | In J1699-5
| 5-10034 | Change INF $F818 evaluation to fail if Recent and Lifetime values are equal or zero for CONV and S/S or warn for HEV and PHEV. | In J1699-5
| 5-10035 | Change INF $F819 evaluation to fail if Recent and Lifetime values are equal or zero for Total and Idle PSA and warn if Recent and Lifetime values are zero or Equal for City PSA. | In J1699-5
| 5-10036 | Change INF $F81A-1C evaluation to warn if Recent and Lifetime values are equal or zero for PHEV. | In J1699-5
| 5-10037 | Change INF $F81D-1F,21-2A evaluation to warn if Recent and Lifetime values are equal or zero and warn if it is supported but all timers are "not available". | In J1699-5
| 5-10038 | Change INF $F841 verification to fail if ERT and EOE Active counters are zero for CONV and S/S or warn if P/HEV, and warn if DT and FC Active counter are zero. | In J1699-5
| 5-10039 | Change INF $F842 verification to fail if Idle Active counters (except Idle FC, see 3-1067) are zero and warn if Engine FC, Idle FC, Urban Speed Run, and PKE counters are zero. | In J1699-5
| 5-10040 | Change INF $F845 verification to fail if ERT and EOE lifetime counters are zero for CONV and S/S or warn if P/HEV, and warn if DT and FC lifetime counter are zero. | In J1699-5
| 5-10041 | Change INF $F846 verification to fail if Idle run time lifetime counter are zero and warn if Engine FC and Idle FC, PKE, and Urban Speed Run counters are zero. | In J1699-5
| 5-10042 | Change INF $F847 verification to fail if Total and Idle PSA time Lifetime counters are zero for P/HEV and warn if Urban PSA Active and Lifetime counters are zero for P/HEV. | In J1699-5
| 5-10043 | Change INF $F848-50 verification to fail if Stored and Lifetime counters are zero for PHEV and warn if Active and Lifetime counters are both zero for PHEV. | In J1699-5
| 5-10044 | Change INF $F851-5B verification to fail if Stored and Lifetime counters are zero. | In J1699-5
| 5-10045 | Change INF $F861-66 verification to fail if Active data is not zero after clear codes command. | In J1699-5
| 5-10046 | Change INF $F867-6C verification to fail if Stored data is zero. | In J1699-5
| 5-10047 | Change INF $F86D-76 verification to fail if Lifetime data is zero. | In J1699-5
Mid May, 2024
| 5-10048 | Test 5.16 - Storing/evaluating of INFs over $7F may cause the application to crash. | In J1699-5
| 5-10049 | The response for SID $22 DID F810 is not evaluated being evaluated. | In J1699-5
| 5-10050 | Add missing newline to end of failure message for DID-Support DID indicating no DIDs supported. | In J1699-5
Late Aug, 2024
| 3-1086 | VerifyInf63_69_6F_73Data must collect the sum of [bin2] through [bin14] and compare to [bin1] for INF $73. | In J1699-5
| 3-1087 | VerifyInf64_6A_70_74Data must collect the sum of [bin2] through [bin14] and compare to [bin1] for INF $74. | In J1699-5
| 3-1088 | VerifyInf65_6B_71_75Data must collect the sum of [bin2] through [bin14] and compare to [bin1] for INF $65, $6B, $71, $75. | In J1699-5
| 3-1089 | VerifyInf66_6C_72_76Data must collect the sum of [bin2] through [bin14] and compare to [bin1] for INF $66, $6C, $72, $76. | In J1699-5
| 3-1090 | Test 9.22 INF $18 - Remove EOE-R, EOE-L, PKE-R, and PKE-L checks for '>0' or comparisons to 5.17 data. | In J1699-5
| 5-10001 | Add support for ETHERNET_NDIS. | In J1699-5
| 5-10051 | How to determine "if equipped" for SID $22 DIDs: $F4AF, F4D3, F4D7, F4AD, F4B0. | In J1699-5
| 5-10053 | Allow NRC $31 when an ECU does not support a physically addressed SID $14 request. | In J1699-5
| 5-10054 | DID $F4CA has been deleted. If supported, do not check size or attempt to decode. | In J1699-5
| 5-10056 | Test 5.16 Fail/Warn messages say "INF $F841 ERT-A must return a value of greater than 1 sec" but should say "INF $F841 EOE-A must…". | In J1699-5
| 5-10057 | Test 5.16 Fail/Warn messages for INF $F854 AT2_TIME_S reports "AT1_TIME-S", AT2_DT-S reports "AT1DT-S", and AT2_DT-L reports "AT1DT-L". | In J1699-5
| 5-10058 | Test 5.16 Fail/Warn when some INFs are set to 0. | In J1699-5
| 5-10059 | J1979-2 indicates that the F4xx, F5xx and F7xx ranges are linked using FxE0 Data D bit 0. | In J1699-5
| 5-10061 | Test 5.10 should not fail if misfire count is greater than 0. | In J1699-5
| 5-10062 | Test 10.10 $19 $1A $91, $19 $1A $93, and $19 $56 $33 $0E all produce a 'response data exceeded buffer size' error. | In J1699-5 |  | MUST USE DYNAMICALLY ALLOCATED MEMEORY, SEE 5-10077
| 5-10064 | Test 5.16 should not FAIL/WARN if $F808/$F80B is not supported. | In J1699-5
| 5-10066 | The function DiaplayPid01() is using data from DID $F501 not $F401. | In J1699-5
| 5-10069 | Test category selection prompts updated to match document. | In J1699-5
| 5-10070 | Incorrect pointer assignment which could prevent evaluation of Protocol ID response. | In J1699-5
| 5-10071 | Correct $F41C range check for greater than or equal to instead of just greater than MAX_OBD_TYPES. | In J1699-5
mid-Nov., 2024
| 3-1102 | Update PID $1C to decode up to $3B. Specifically add Brazil OBD Phase 8 (PID 1C with value of $2F) and Brazil OBD Phase 7 with IUMPR (PID 1C with value of $2A). | In J1699-5
| 3-1103 | The prompt for Vehicle Type says "3 Medium Duty Truck Engine Dyno Certified (< 1400 lbs GVWR)", but it should be 14000. | In J1699-5
| 3-1104 | Test 10.12 The prompt should say "(BARO > 22 in Hg)", but it currently says "(BARO < 22 in Hg)". | In J1699-5
| 5-10022 | Add ZEV DID Validation Tests. | In J1699-5
| 5-10060 | Test 6.4 (in log; 6.3 in doc) FAILED for a Type A (first trip) DTC, but it should not. | In J1699-5
| 5-10063 | Test 10.10 needs to clearly identify what to do with a broadcast request for a Readiness Group that is not supported by the vehicle. | In J1699-5
| 5-10067 | Test 10.3 is failing without a FAILURE being logged, where we get an NRC for SID $22 DID $F8A0, because it is not supported. | In J1699-5
| 5-10068 | Test 5.16 Fail if $F878 Engine Rated Power and Engine Rated Speed are set to 0. | In J1699-5
| 5-10074 | Prompt Q02 Add "ICE" to the #1 and #2 selections. | In J1699-5
| 5-10075 | Test 5.6 Compares single responses to group responses and falsely fails because not all groups have been requested. | In J1699-5
| 5-10076 | Test 5.6 No FAILURE is flagged if an ECU indicates support for the next DIDSupported DID, but that DIDSupported DID is not supported. | In J1699-5
| 5-10077 | Test 10.10 Still getting 'Response exceeded buffer size' messages from $19 $1A $93, $19 $56 $33 $0E. | In J1699-5 | TEMP WORK-AROUND IMPLEMENTED
| 5-10078 | Remove protocol check from Tests 5.8, 6.2, 7.2, 8.2, 9.2, 9.9, 9.13, 9.17, and 9.21. | In J1699-5
| 5-10080 | Test 5.4 requests SID $01 PID $00, but SID $01 PID $01 is required. | In J1699-5
| 5-10081 | Test 5.4 The evaluation of SID $22 DID $F501 depends upon DIDSupported DIDs, but they not currently being requested. | In J1699-5
| 5-10083 | Test 5.6 should FAIL if DID $F401 is supported. | In J1699-5
| 5-10085 | Warnings for $F841 EOE should have the units of MWh NOT sec. | In J1699-5
| 5-10086 | Warnings for $F845 EOE should have the units of GWh NOT sec. | In J1699-5
| 5-10087 | In Test 5.16 (can be 200 sec after clear codes) a Warning/Failure for $F841 VFC-A, $F842 EFC-A, and IEFC-A when value is 0 does not make sense. | In J1699-5
| 5-10090 | Require NRC for a functional SID $22 DID $F401, $F402, $F441 - if not supported. | In J1699-5
| 5-10092 | Test 5.17 Group Request versus Single Request for DID $F501 reports: SID $22 group/single DID size mismatch (Response = 8 bytes Expected = 26554 bytes) | In J1699-5
| 5-10094 | Fail if no NRC for a physical request of a DID that is not supported. | In J1699-5
| 5-10096 | Test 12 Add support CAN on ZEVs. | In J1699-5
Late Dec. 2024
| 5-10073 | Add ZEV Fault Insertion tests.
| 5-10093 | In Test 5.16 the overall test FAILs but no faiure is noted for a specific item (in the log). However, there are WARNINGs noted.
| 5-10095 | Add Freeze Frame functionality for ICE.
| 5-10097 | Test 10.7, Add support for Test Results (SID $22 $F6xx).
| 5-10098 | Test 10.11 - Crash because ECU IDs don't match original list.
| 5-10099 | Test 7.4 Fails if all F501 responses don't indicate that MIL is active. |  |  | DOCUMENTATION QUESTION
Later
| 3-1014 | Support for CNG engines in J1699. | J1699-5 Needs This |  | NEED DOC
| 3-1046 | Define a new test for a group PID requests containing a known unsupported PID. | J1699-5 Needs This |  | NEED DOC
| 3-1056 | Test 5.9, Not all ECUs respond to SID $04, but no error is flagged. | J1699-5 Needs This |  | NEED DOC
| 3-1050 | There is a large time gap between request and receive. | J1699-5 Needs This |  | NOT ABLE TO DUPLICATE
| 3-1101 | Add more detail to explaination of "Protocol determination unsuccesful". | J1699-5 Needs This
| 5-10018 | Test 5.5 / Test 5.13 F6xx Validation; Check for supporting what you say you support and verify response size… no test result validation. |  |  | NEED DOC
| 5-10020 | Allow NRC $22 (Conditions Not Correct) for SID $22 under EOBD. |  |  | NEED DOC
| 5-10021 | Support SMAD (INF $92-$93) in Mfg. Specific Drive Cycle. |  |  | NEED DOC
| 5-10055 | NRCs allowed may change based on powertrain or Complinace Type. |  |  | NEED DOC
| 5-10065 | Support non-OBD II Compliance Types. |  |  | NEED DOC
| 5-10072 | Support multiple edge nodes on DoIP.
| 5-10089 | DoIP Routing Activation is failing on a ZEV. |  | HOLD MAY BE A VHEHICLE ISSUE
DOC ISSUES
| 5-10084 | The document is not clear... are NRC allowed for Functional Requests? |  | FIXED IN DOC

## J1699-5 Software History
Validated by OEMs | Date Recommended to CARB | Document Version | Software Version | Software Date | J2534 API Version | Initial Model Year Targeted | Comments on Software
NO |  | 4.4 | 04.04.00 | 2024-11-13 | 0404 | 2024 | Update PID $1C to decode up to $3B; Add ZEV/ACC-II DID Validation Tests; Do not fail a broadcast request for a Readiness Group that is not supported; Add Fail if $F878 Engine Rated Power and Engine Rated Speed are set to 0; Add "ICE" to Prompt Q02 selections #1 and #2 and "ACC II" PHEV to #3; Remove Warning/Failure for $F841 VFC-A, $F842 EFC-A, and IEFC-A == to 0; Add support for the requirement that a functional request of DID $F401, $F402, $F441 should fail if it does not receive a NRC $31, if not supported; Add support for the requirement that unsupported DID requests should respond with NAK $31 in physical addressing (and $F401, $F402 and $F441 in functional addressing); Add support for CAN on ZEV;Fix the prompt for Vehicle Type to say "3 Medium Duty Truck Engine Dyno Certified (< 14,000 lbs GVWR)", instead of "1400"; Fix the prompt in Test 10.12 to say "(BARO > 22 in Hg)", instead of "(BARO < 22 in Hg); Fix failing for a Type A (first trip) DTC, in Test 6.3; Log FAILURE when an NRC $31 is received for DID-Support DID request because it is not supported; Improve group requests to continue to request even if there were problems to reduce fails in single response comparison; Fail if an ECU indicates support for the next DID-Support DID, but that DID-Support DID is not supported (no response); Add support for up to 1024 DTC IUMPRs, SMAD and IM Readiness list entries (number of entries in a 4k msg); Remove DetermineProtocol test from all but 5.1, 10.1, and 12.1; Test 5.4 should request deprecated SID $01 PID $01 instead of PID $00 in Test 5.4; Request PID-Support PIDs before physically addressed request of SID $22 DID $F501, if they have not been populated yet; FAIL if DID $F401 is supported; Change the units in the Warnings for $F841 EOE-A from sec to MWh; Change the units in the Warnings for $F845 EOE-L from sec to GWh; Fix false failure when less than 3 PIDs are supported in $F5xx range, causing group/single DID size mismatch.
NO |  | 4.0 | 04.00.00 | 2024-08-28 | 0404 | 2024 | Added Bin summing for INFs $F866, $F865, $F86B, $F86C, $F871, $F872, $F873, $F874, $F875, $F876; Test 9.22 INF $18 - Remove EOE-R, EOE-L, PKE-R, and PKE-L checks for '>0' or comparisons to 5.17 data; Add support for ETHERNET_NDIS; Remove validation "if equipped" for SID $22 DIDs: $F4AF, F4D3, F4D7, F4AD, F4B0; Allow NRC $31 when an ECU does not support a physically addressed SID $14 request; Test 5.16 Fail/Warn messages say "INF $F841 ERT-A must return a value of greater than 1 sec" but should say "INF $F841 EOE-A must…"; Test 5.16 Fail/Warn messages for INF $F854 AT2_TIME_S reports "AT1_TIME-S", AT2_DT-S reports "AT1DT-S", and AT2_DT-L reports "AT1DT-L"; Test 5.16 Fail/Warn when some INFs are set to 0; J1979-2 indicates that the F4xx, F5xx and F7xx ranges are linked using FxE0 Data D bit 0; Test 6.4 (in log; 6.3 in doc) FAILED for a Type A (first trip) DTC, but it should not; Test 5.10 should not fail if misfire count is greater than 0; Test 10.10 $19 $1A $91, $19 $1A $93, and $19 $56 $33 $0E all produce a 'response data exceeded buffer size' error; Test 5.16 should not FAIL/WARN if $F808/$F80B is not supported; The function DiaplayPid01() is using data from DID $F501 not $F401; Test category selection prompts updated to match document; Incorrect pointer assignment which could prevent evaluation of Protocol ID response; Correct $F41C range check for greater than or equal to instead of just greater than MAX_OBD_TYPES.
NO |  | 3.5 | 03.05.01 | 2024-05-13 | 0404 | 2023 | Fixed Test 5.16 - Storing/evaluating of INFs over $7F may cause the application to crash; The response for SID $22 DID F810 is not evaluated being evaluated; Add missing newline to end of failure message for DID-Support DID indicating no DIDs supported.
NO |  | 3.5 | 03.05.00 | 2024-04-25 | 0404 | 2023 | Fixed Using J1699_CONFIG.INI; Test 5.17 issues; SID $09 INF $47; SID $01 PID $A3; Q03 Prompt needs to accept >2025 MY; Q10 Prompt needs to accept more than one digit; INFs $16-$29 are checked for max. value or "not available"; Implement J1699-5 specified Dynamic Test (IUMPR equivalent); PID Supported PIDs F4E0 and F5E0 should both have bit 0 set to 0; SID $22 $F503 and $F505; Add size checks for PID $F4A7,A8,AA,AC-B1,C3,C7,C9,CB,CF,D3,D7; Comment out MID tests; Added/changed a bunch of INF $F8xx items.
NO |  | 2.6 | 02.06.01 | 2023-11-08 | 0404 | 2023 | Removed Test 5.11 of J1699-5, FreezeFrame data shall be requested a SERVICE $19 SUBSERVICE $04. The SW actually requests SERVICE $19 SUBSERVICE $03 instead; Changed Europe and China compliance types to better match document; Added definitions for EnergyType and FuelType and remove EngineType and gbDiesel to match document; Fixed SID $09 INF $78 should only apply to diesel MD, MDDC, and HD; Fixed Test 5.17 for SID $09 INF $77 should WARN for 2022-2023 and FAIL for 2024, but currently FAILs; Fixed false fail for unsupported signals in tracking INFs like $17 in EU; Fixed Test 5.8 ends when there is no response to PID $F40D on 29-bit, but a link monitor shows there was a response; Fixed When testing on a light duty car, J1699-5 requires heavy duty PIDs to be present; Fixed Test 5.10 evaluation of PID $F501 issues with engine running; Fixed Byte #4 in a Freeze Frame Response should be $FF, but J1699-5 expects $04. Test 5.14 / Test 8.3 / Test 9.3 with a false WARNING; Fixed Test 5.6 is failing all ECUs if they do not support EGS, CV, EGR, CSER.
NO |  | 2.6 | 02.06.00 | 2023-08-07 | 0404 | 2023
NO |  | 2.3 | 02.03.00 | 2023-03-14 | 0404 | 2023 | Test 5.17 GHG INF requirements apply to all HD Vehicles. Should also consider the type of Regulatory/Engine/Powertrain; China6 does not require all or nothing when clearing codes like OBD II does (e.g., during KOER); Test 5.18 incorrectly flags the response to a SID $01 PID $E0, $C0 group request as a failure if $E0 is not supported; In the Dynamic Test, after logging the meta information, it starts somewhere within Test 10.3... So, Tests 10.1 and 10.2 are missing completely, the same is true for the first part of Test 10.3; False failure in Test 5.17 for missing INF $78. This should be for HD and MD only, not LD; Extra space added between "*" and "T" (+000000ms RESULTS: **** Test 5.1 PASSED ****), which breaks tools. It needs to be added back; Test 11.2 with implausible data for initial IUMPR; Test 9.19 and 11.2 crash with China6 selected; Test 11.2 waiting for Bank2 to complete, when vehicle only has Bank1; Clarify wording in Q03 to indicate it is VIN Model Year; Clarify wording in the phase-in WARNING for new INFs; Test 5.6, PID $A1 has an incorret data transformation; Fix display resolution loss in calculation of PID $85 and $96; Change TEST 11.2 on-screen text from RESERVED to GPF for gasoline vehicles; Protocol determination uses SID $01 PID $00, but it should use SID $22 PID $F810.
NO |  | 1.4 | 1.00.00 Beta | 2022-04-15 | 0404 | 2023 | Port of J1699-3 V17.01.00 to UDS.

## Software Change Process
1 | When making changes to the software, strictly follow the requirements in the SAE J1699-3 document.
2 | Do not alter the tests or evaluation criteria defined in the J1699-3 document based on requests from OEMs, suppliers, or other interested parties. In these cases, flag the request and bring it to the attention of Task Force. The software shall only be changed if the J1699-3 document also changes.
3 | In cases where the J1699-3 document is alleged to be inconsistent with the regulations, flag the issue and bring it to the attention of Task Force. Do not attempt to interpret the regulations and do not act independently to alter the software. The software shall only be changed if the J1699-3 document also changes.
4 | Document software changes (whether they are driven by a document change or a bug fix) in SourceForge. All new SourceForge issues shall be discussed during the Software Update portion of each SAE J1699-3 Task Force meeting. Include this information as attachments to the meeting minutes so that it can be distributed to all Task Force members. Work to insure that all known deviations and software bugs are documented in SourceForge.

## Software Version Number
The software version number has the following format: aa.bb.cc[.dd] where aa is the major version number of the J1699-3 document where the implemented requirements are drawn from. bb is the minor version number of the J1699-3 document where the implemented requirements are drawn from. cc is the software update level for the associated aa.bb branch (bug fixes when there has been no change the document where the implemented requirements are drawn from). dd is only used for Beta Test releases (that is, un-official versions), this number started at 0 and increments by one until the official release at which time it is to be removed. The '.dd' is just present to differentiate the Beta Test versions from the 'official' version.